# draa

# Proactive Care Coordination Assistant (PCCA) Integration Guide

To be used by PCN Improvement Facilitator to plan clinic-specific processes related to a new PCCA starting at a clinic.

Contents

Introduction to the PCCA Role	2

Timeline for Integrating a PCCA into a New Clinic	3

Clinic Requirements for PCCA Services	4

Guiding Questions on Clinic Paneling Processes	4

PCCA Process Checklist	5

Clinic Requests Outside of Standard PCCA Protocol	8

## Introduction to the PCCA Role

Proactive Care Coordination Assistants (PCCAs) are administrative staff who work “behind the scenes”, using a clinic’s EMR. This position is offered to all ESPCN clinics with EMRs, which allow us to pull reports, and is offered in addition to their MDT budget.

The PCCA program is a safety net to prevent vulnerable patients from falling through the cracks in our health system.

PCPs receiving PCCA support observe improvements in their EMR preventative health screening rates, patient continuity of care, and panel accuracy.

On a 12-week schedule, PCCAs rotate between multiple clinics for blocks of time, from 1-12 weeks, as determined by a clinic’s panel size.

PCCAs find patients who are due for care or screening, including patients who are:

- On a CPAR Conflict list as attached to multiple providers

- Under 18 years of age and have not had an appointment in 2 years or more

- 18-74 years of age and have not had an appointment in 3 years or more

- 75+ years of age or have a chronic disease and have not had an appointment in 1 year or more

- Due for screening for: breast/cervical/colorectal cancer, diabetes, or plasma lipid profile.

PCCAs call patients to offer an appointment with their PCP or the appropriate MDT, or a screening requisition, depending on the process the clinic develops with their IF.

## Timeline for Integrating a PCCA into a New Clinic

| Timeline | Involved | Actions |
| --- | --- | --- |
| Prior to PCCA Starting | Improvement Facilitator and Primary Care Manager | - IF and PCM meet with clinic to discuss role. Discuss Clinic Requirements for PCCA Services. - IF may work with EMR-C to complete EMR Assessment (excel template) and Guiding Questions on Clinic Processes (Optional) - IF will complete Process Checklist (required) and inform PCC Lead of clinic’s readiness. - IF will add clinic information into PCCA Weekly Tracking Sheet (excel template), including tab for Clinic Process Manual (see template). |
|  | PCC-Lead and QIM | - Match PCCA to clinic, considering language, rotation requirements. - Update PCCA Rotation Schedule with new clinic. |
|  | IF & PCM & Clinic | - IF or PCM will also ensure clinic arranges an EMR account with remote access, and Netcare access. |
|  | EMR-C | - Develop EMR queries related to all required reports. - Activate EMR alerts for the 5 diagnostic preventative health screens. - Create task templates for tracking chart reviews and outreach calls. - Save screenshots of EMR queries into PCCA Teams folder. |
| PCCA Initial Visit | IF | - Join PCCA for initial visit, introducing them to the clinic team and ensuring they can sign into EMR. - Share relevant findings with clinic, gain feedback, and modify processes accordingly. |
| Annually | IF | - Email EMR data to PCPs. - Share relevant findings with clinic, gain feedback, and modify processes accordingly. |

## Clinic Requirements for PCCA Services

- Clinic is live or in the process of enrolling to CII/CPAR

- Clinics must allow PCCA to perform outreach phone calls to arrange appointments or offer patients screening requisitions.

- Clinics must define who they consider an attached patient and have a process to differentiate consultative or walk-in patients.

- PCCAs will confirm on Netcare that screening has not been completed elsewhere. If previous screens have been completed, the chart will be updated to satisfy EMR Notification.

- PCCA requires access to functions in EMR that allow reports to be generated.

- Clinics will set up EMR login for EMR Consultant and PCCA, with remote login and appropriate access enabled at least two weeks prior to the PCCA’s start date.

- Clinics will arrange Netcare access for PCCA at least one week prior to their start date.

## Guiding Questions on Clinic Paneling Processes

Discussion between IF and Clinic Office Manager

| Questions | Recommended Process |
| --- | --- |
| Walk-ins How does the team differentiate walk-in from panelled patients in EMR? | Ensure clinic is using accurate paneling processes. |
| Statuses What EMR statuses (most EMRs) or End Date Reasons (HQ) does the clinic use? - Name of status: - Purpose: - Does the clinic use End Date? (HQ) | Some HQ clinics do not End Date patients, as they need to be searched by PHN if they return. These clinics may use an alternate status for inactive patients, or move them to “Walk-in” status. |
| Chart Transfers Have any PCP’s joined the practice, transferring charts from a previous clinic? If so, how did the charts transfer over (was information scanned into one file, or did it integrate into current EMR chart)? | Ensure we are capturing correct panel by pulling a PCP’s active patients. Ensure details in charts will pull into our reports (last visit date, results). |
| PCP How are default PCPs assigned in the EMR? Does the clinic confirm attachment with each patient visit? What do they ask patients? How is it done in the EMR? | Explain benefits of recommended process of confirming attachment, demographics, and validating in EMR at every visit. |

## PCCA Process Checklist

PCP: _______________________

Initial Panel Clean-up of Patients with no visit in 3+ years (all ages):

☐ Batch inactivate without calling (recommended) OR

☐ PCCA will contact patients to confirm attachment and offer an appointment (confirm list is <500 patients)

Future rotation inactivation of patients not seen in 3+ years:

If a patient has not been seen in 3+ years, PCCA will:

☐ Inactivate them

☐ Call them once, and then inactivate them on their next rotation if they have not booked an appointment or confirmed attachment.

Booking Rules

Main Process

☐ PCCA will call and book appointments (required)

☐ Front staff understand PCCA will leave open worklists, addressed to themselves, if they leave a message to patients or closed worklists if they book an appointment. Clinic team understand to check those appointment if patient calls back, or if patient attends appointment.

☐ Maximum number of complete physicals/screening appointments per day: __________

☐ Clinic/PCP-specific rules around scheduling:  _______________________________

☐ Other: _____________________

How will patients be inactivated:

☐ Remove Primary Provider/Default PCP OR

☐ End Date or End Date Reason (HQ) OR

☐ Change Status OR

☐ Process for patients with no active contact information on file: ____________________

Pediatric Outreach of patients with no visit in 2+ years (0-17):

☐ PCCA to contact patient and confirm attachment with PCP and pediatrician, and offer appointment if needed

☐ PCCA to record pediatrician name in the EMR: _______________________________

Adult Outreach of patients with no visit in 3+ years (18-74):

☐ PCCA will contact patients to confirm attachment and offer an appointment (recommended for clinics providing longitudinal care for several years) or

☐ PCCA will inactivate patients without calling (recommended for clinics with transient panels or who juts recently began paneling processes).

High risk patients with no visit in 1+ year:

- Patients age 75+

- Patients with diabetes, hypertension, COPD, CHF, heart disease, or kidney disease

☐ PCCA will check CPAR Demographic Mismatches and inactivate patients who are deceased, prior to running this list. If PCP is not on CPAR yet, PCCA will check Netcare for deceased status.

If an Active patient is listed as Deceased, should PCP be notified by worklist/task?  ☐ yes ☐ no

☐ Appointment type for recall (e.g., complete medical exam): _____________________

Screening Outreach

☐EMR-C will activate EMR notifications for patients due for the 5 preventative health screens.

PCCA will:

☐ Recall all patients overdue for screening (no time modifier)

☐ Type information into template/task (recommended)

☐ Investigation date only (recommended)

☐ Investigation date and results including name of ordering PCP. OR

☐ Download external results into EMR (required in Ava, CHR, Accuro, but not otherwise recommended)

☐ Inform PCP about abnormal external results via task/worklist (required)

☐ Recall patients who are due for preventative screening.

| Screens | Appointment Type |
| --- | --- |
| Mammo, CRC, Diabetes, Lipids, Pap | ☐ Book CME screening appointment with PCP or RN, as appropriate. ☐ Book Paps with RN ☐ Requisition Protocol* |
| *Requisition Protocol (recommended) | ☐ Mammogram ☐ FIT ☐ Diabetes ☐ Lipids Process: ☐ eFax requisition to patients’ preferred lab/imaging ☐ Print for patient pick up from clinic ☐ Send through patient portal ☐ Other: ___________________________ |

CII/CPAR

Onboarding status

☐ Clinic not participating (ineligible for PCCA)

☐ Clinic is Live

Access Administrator

☐ MD

☐ Clinic Manager

Panel Administrator (PA)

☐ Clinic staff:________

☐ PCCA

Recommended that both PCCA and clinic staff/office manager be joint-PAs.

Conflict Management Process

☐ PA will call patients to confirm attachment.

☐ PA will eFax letter to conflicting clinic to request patient to be unpaneled.

☐ PA will worklist/task the front staff to fax letter to conflicting provider.

☐ PA will unpanel patients who confirm attachment elsewhere.

Demographic Mismatch Process

☐ Report shared with clinic to be worked on opportunistically.

Data management process

☐ PCCA works off downloaded list and does not save.

☐ PCCA saves the list under a test patient as an attachment.

☐ PCCA saves list in their work OneDrive for the duration of the rotation (deletes end of rotation)

☐ Other ________________________

Data Sharing

☐ As PCN funding requirement, PCCA will collect panel and screening data, and send to PCN to be aggregated (all identifying information removed) and submitted to Alberta Health

☐ Date IF and PCP will meet to review data and modify plans: ___________________

☐ Can we request HQCA proxy panel on behalf of the PCP? Best email:______________

## Clinic Requests Outside of Standard PCCA Protocol

IFs may encounter requests that are outside of standard recommendations. Some can be accommodated if they achieve the purpose of supporting at-risk or vulnerable populations. Others may be redirected back to clinics to support, particularly if their intention is to generate financial revenue, or they are not evidence-based. Common requests are detailed below.

- Clinics request a longer interval for calling patients who have not been to their clinic, such as 5 years instead of 3. Typically, 95% of patients not seen in 3 years are no longer active. We do still call these patients as we want to capture that 5% but extending this is not a good use of the PCCA’s time. If the clinic feels this is a priority, we can provide their staff the list of patients not seen in over 4 years, to review and call, prior to the PCCA starting.

- PCP requests to review the lists before a PCCA calls a patient. The IF should inquire what the concerns behind this request are and address them by: introducing the PCCA to the PCP, explaining their training and role, reassure the PCP that the PCCA will always defer to them if there are any clinical decisions. If the PCP still wants to review the list first, we would support them in pulling the list, but would wait until they have reviewed and returned this list before starting PCCA work at the clinic. If the PCCA has already started and the list is not ready, the PCCA may end their rotation early, and support another clinic.

- Clinic/PCP requests all patients be recalled for yearly physicals, regardless of whether they are due for screens: IF should explain that the PCCA role is to focus on higher risk groups. If the clinic also wants to complete yearly physical outreach, they could work on this separately. Our EMR-C can help them build a report or EMR alert to identify these patients.

- PCP requests additional criteria (e.g., all patients over 50 to be called annually, all patients due for PSA, all patients due for CMEs): IF should inform that PCCA role is to focus first on our high risk groups and provincially identified maneuvers. IF may seek clarification from QI Manager if additional group fits into PCCA scope of practice. For screening beyond 5 diagnostic screens that PCCA recalls (e.g., PSA, AAA) or immunizations, we may offer to turn on EMR alerts so the clinic can capture these patients opportunistically.

- PCP requests variations to outreach criteria (e.g., cervical cancer screening to start at 30 instead of 25): If these variations do not violate screening guidelines, they can be accommodated. We will still collect annual data using provincial eligibility criteria. If request appears to violate screening guidelines (e.g., cervical cancer screening to start at 20 instead of 25), IF may discuss with clinic, referencing guidelines, and that PCCA would not be able to support this work. IF may consult with QI Manager about specific requests.